## crm_internal_checklist
Task | Hours
Design entity 'person' (abstract, base for PF/PJ) | 2
Design 'person_individual' (PF) | 2
Design 'person_company' (PJ) | 2
Design 'contact' entity | 2
Design 'account' entity | 2
Define relation: contact ↔ account | 2
Implement CRUD: Accounts (companies) | 3
Implement CRUD: Contacts (individuals) | 3
Logic to link/unlink Contacts to Accounts | 2
Contact form (create/edit) | 2
Account form (create/edit) | 2
View contacts by account | 2
Contact detail view | 2
Design 'opportunity' entity: value, close date, stage, etc. | 2
CRUD: Opportunities | 3
Link Opportunity to Contact and/or Account | 2
Logic: Update stage with drag-and-drop | 2
Visual board with columns per stage | 3
Implement drag-and-drop logic | 3
Opportunity card with basic info | 2
Entity 'lead': source QR/site/manual | 2
Entity 'activity': call, meeting, email | 2
Entity 'document' linked to customer or opportunity | 2
Auto-create lead via QR code | 3
Handle lead via site (manual or API) | 2
Manual lead input | 1
Register sales activities (linked to contact/account) | 2
Upload/download documents | 3
Manual lead form | 2
Activity tracking dashboard | 2
Document upload interface | 2
Document list by client/opportunity | 2
Sales funnel report with stage conversion | 4
Forecast based on opportunity data | 4
Performance per salesperson | 4
Activity summary per user | 4
Lead source analysis | 3
Funnel and forecast charts | 3
Ranking and sortable tables | 3
Filters by period, status, user | 2
Simple export to PDF/Excel | 2
Test all user flows | 3
Validate business rules | 3
Fix UI bugs | 3
Final visual adjustments and responsiveness | 3
Improve usability (UX details, shortcuts, messages) | 3
Light documentation for use | 3
Initial DB backup and delivery prep | 2
119