## crm_internal_checklist_numbered
Task | Hours
1.1 Design entity 'person' (abstract, base for PF/PJ) | 2
1.2 Design 'person_individual' (PF) | 2
1.3 Design 'person_company' (PJ) | 2
1.4 Design 'contact' entity | 2
1.5 Design 'account' entity | 2
1.6 Define relation: contact ↔ account | 2
1.7 Implement CRUD: Accounts (companies) | 3
1.8 Implement CRUD: Contacts (individuals) | 3
1.9 Logic to link/unlink Contacts to Accounts | 2
1.10 Contact form (create/edit) | 2
1.11 Account form (create/edit) | 2
1.12 View contacts by account | 2
1.13 Contact detail view | 2 | 28
2.1 Design 'opportunity' entity: value, close date, stage, etc. | 2
2.2 CRUD: Opportunities | 3
2.3 Link Opportunity to Contact and/or Account | 2
2.4 Logic: Update stage with drag-and-drop | 2
2.5 Visual board with columns per stage | 3
2.6 Implement drag-and-drop logic | 3
2.7 Opportunity card with basic info | 2
3.1 Entity 'lead': source QR/site/manual | 2
3.2 Entity 'activity': call, meeting, email | 2
3.3 Entity 'document' linked to customer or opportunity | 2
3.4 Auto-create lead via QR code | 3
3.5 Handle lead via site (manual or API) | 2
3.6 Manual lead input | 1
3.7 Register sales activities (linked to contact/account) | 2
3.8 Upload/download documents | 3
3.9 Manual lead form | 2
3.10 Activity tracking dashboard | 2
3.11 Document upload interface | 2
3.12 Document list by client/opportunity | 2
4.1 Sales funnel report with stage conversion | 4
4.2 Forecast based on opportunity data | 4
4.3 Performance per salesperson | 4
4.4 Activity summary per user | 4
4.5 Lead source analysis | 3
4.6 Funnel and forecast charts | 3
4.7 Ranking and sortable tables | 3
4.8 Filters by period, status, user | 2
4.9 Simple export to PDF/Excel | 2
5.1 Test all user flows | 3
5.2 Validate business rules | 3
5.3 Fix UI bugs | 3
5.4 Final visual adjustments and responsiveness | 3
5.5 Improve usability (UX details, shortcuts, messages) | 3
5.6 Light documentation for use | 3
5.7 Initial DB backup and delivery prep | 2
119