## crm_internal_checklist_numbered
1.1 Design entity 'person' (abstract, base for PF/PJ) | 2,62h
1.2 Design 'person_individual' (PF) | 2,62h
1.3 Design 'person_company' (PJ) | 2,62h
1.4 Design 'contact' entity | 2,62h
1.5 Design 'account' entity | 2,62h
1.6 Define relation: contact ? account | 2,62h
1.7 Implement CRUD: Accounts (companies) | 2,62h
1.8 Implement CRUD: Contacts (individuals) | 2,62h
1.9 Logic to link/unlink Contacts to Accounts | 2,62h
1.10 Contact form (create/edit) | 2,62h
1.11 Account form (create/edit) | 2,62h
1.12 View contacts by account | 2,62h
1.13 Contact detail view | 2,62h
2.1 Design 'opportunity' entity: value, close date, stage, etc. | 4,00h
2.2 CRUD: Opportunities | 4,00h
2.3 Link Opportunity to Contact and/or Account | 4,00h
2.4 Logic: Update stage with drag and drop | 4,00h
2.5 Visual board with columns per stage | 4,00h
2.6 Implement drag and drop logic | 4,00h
2.7 Opportunity card with basic info | 4,00h
3.1 Entity 'lead': source QR/site/manual | 3,17h
3.2 Entity 'activity': call, meeting, email | 3,17h
3.3 Entity 'document' linked to customer or opportunity | 3,17h
3.4 Auto create lead via QR code | 3,17h
3.5 Handle lead via site (manual or API) | 3,17h
3.6 Manual lead input | 3,17h
3.7 Register sales activities (linked to contact/account) | 3,17h
3.8 Upload/download documents | 3,17h
3.10 Activity tracking dashboard | 3,17h
3.9 Manual lead form | 3,17h
3.11 Document upload interface | 3,17h
3.10 Activity tracking dashboar | 3,17h
3.12 Document list by client/opportunity | 3,17h
3.11 Document upload interface | 3,17h
3.12 Document list by client/opportunity | 3,17h
5.1 Test all user flows | 4,29h
5.2 Validate business rules | 4,29h
5.3 Fix UI bugs | 4,29h
5.4 Final visual adjustments and responsiveness | 4,29h
5.5 Improve usability (UX details, shortcuts, messages) | 4,29h
5.6 Light documentation for use | 4,29h
5.7 Initial DB backup and delivery prep | 4,29h